## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Data Visualisation and analytics of Employee Data for Cloud Counselage
PROJECT SPONSOR | None
PROJECT MANAGER | Cloud Counselage pvt.ltd.
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST | None
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main Objective of this Data Science Project is to collect and process the encoded and missing data of the interns in Cloud Counselage and gather insights from it. This research and Visualisation project will help Cloud Counselage understand their interns' background etc and further assist in hiring interns for subsequent needs.
BUSINESS CASE | Over the years, Cloud Counselage has been on a mission to develop and groom freshers and professionals PAN India to become IT and Management pioneers. To accomplish this mission, we have come up with a solution, a job portal that will list down the jobs available in major companies across India. Also, one of the success criteria of career services that Cloud Counselage offers is to get our interns placed in a job of their interest with us or with our partner companies and we will, therefore, ensure that the interns of Cloud Counselage will be given the priority for the jobs over the others and these jobs will be procured using the Job Cloud platform.
GOALS/METRICS | To perform preprocessing on the raw data and gather useful insights to form meaningful conclusions via data visualisation techniques
EXPECTED DELIVERABLES | A detailed case study comprising of various visualisation methods highlighting the essential insights gathered from the data
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Data visualisation models to visualise and gather insights from the data based on the requirements
OUTSIDE OF SCOPE | Machine learning model to predict whether the intern is fit for recruitment based on intern's details
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Vedant Nitin Deshpande
SUPPORT RESOURCES | Workstation/Laptop with discrete Graphics, Code Editor and Environment
SPECIAL NEEDS | Stable Internet Connectivity
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Vedant Nitin Deshpande
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
EXPECTED BENEFIT | Ability to screen, manage and visualise various metrics regarding interns of Cloud Counselage for further actions
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Techical risk:Unmet requirements-forgetting to include a single requirement can cost us time & budget overhead, or worse, poor product quality. Resource risk:Uncertainty in resource availability: Interns might go on leave on commencement of university exams. Due to the COVID-19 outbreak, the exact examination dates are not available.On team change over, new members needs to get trained and it's time-consuming. Also, the current team members lack knowledge in back-end development. This might result in the escalation of project completion.
ASSUMPTIONS
CONSTRAINTS | Very stringent time for the completion of the project, Unavailability of resources due to COVID-19 scenario