## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Data Visualisation model
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-07
PROJECT DELIVERABLE | Case study on Intern Dataset |  | EXECUTION PHASE END DATE: |  | 2020-07-27
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-06-15 | 2020-07-01 | 16 | COMPLETED
| 1.2 Recruit a team |  | 2020-06-16 | 2020-07-01 | 16 | COMPLETED
| 1.3 Create a project charter |  | 2020-06-17 | 2020-07-01 | 16 | COMPLETED
| 1.4 Requirement gathering |  | 2020-06-18 | 2020-07-01 | 16 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-07-01 | 2020-07-07 | 6 | COMPLETED
| 2.2 Baseline project plan |  | 2020-07-01 | 2020-07-08 | 7 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-07-01 | 2020-07-09 | 8 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-07-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | COMPLETED
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
| 3.2.1.1 Data Preprocessing and Cleaning |  |  | 2020-07-07 | 7 | COMPLETED
| 3.2.1.2 Initial loading and visualisation of data |  |  | 2020-07-13 | 8 | COMPLETED
| 3.2.1.3 Data Visualisation and Gathering insights from data |  |  | 2020-07-20 | 12 | COMPLETED
| 3.2.1.4 Drawing Conclusions from the visualisation models |  |  | 2020-07-25 | 3 | COMPLETED
| 3.2.1.5 Perform Label Encoding on Data |  |  | 2020-07-26 | 1 | COMPLETED
| 3.2.1.6 Passing data to various Classifiers and getting performance data |  |  | 2020-07-28 | 2 | COMPLETED
| 3.2.1.7 Finalising results and selecting best classifier |  |  | 2020-07-29 | 1 | COMPLETED
| 3.3 Testing |  | 2020-07-25 | 2020-07-31 | 6
| 3.3.1 Manual testing |  |  |  |  | COMPLETED
| 3.3.2 Automation testing |  |  |  |  | COMPLETED
| 4 Closure |  | 2020-07-31 | 2020-07-31 | 1 | COMPLETED