## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | Data Science Visualisation project
PROJECT ID | LIVE PROJECT
PROJECT MANAGER | Jayanth G S
DOCUMENT VERSION | 1
PROJECT START DATE | 2020-07-01
PROJECT END DATE | 2020-07-30
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Visualisation Model |  | 2020-07-12 |  |  |  | Completed
2 | Graphs and ddata cleaning |  | 2020-07-20 |  |  |  | COmpleted
3 | Label Encoding |  | 2020-07-23 |  |  |  | Cpmpleted
4 | Model initiation |  | 2020-07-25 |  |  |  | Completed
5 | Model Finalisation |  | 2020-07-27 |  |  |  | Completed
6 | Project Submisssion |  | 2020-07-30 |  |  |  | IN Progress