## OVERVIEW
MINOR PROJECT MANAGEMENT METHODOLOGY
BACKGROUND
Cloud Counselage delivers many projects for its clients and internally as well. To bring about consistency in the way we deliver our projects, we have developed a project management methodology, which helps our client and our team understand the approach that needs to be taken to deliver these projects. Since these projects vary in duration depending upon its scope, it is practical to take a different approach to deliver projects which are of shorter duration than that taken for the projects of longer duration to bring about efficiencies. In CLoud Counselage, the projects of more than 3 months duration is referred to as major project and that upto 3 months duration is referred as minor project.
OBJECTIVE
The objective of this document is to
PROJECT OVERVIEW
A project is a unique endeavor to produce a set of deliverables within a clearly specified time, cost, and quality constraints. Projects are different from standard business operational activities as they; * Are unique in nature. They do not involve repetitive processes. Every project undertaken is different from the last, whereas the operational activities often involve undertaking repetitive(identical) processes. * Have a defined time scale. Projects have a clearly specified start and end date within which the deliverables must be produced to meet specified customer requirements. * Have an approved budget. Projects are allocated a level of financial expenditure within which the deliverables are produced, to meet a specified customer requirement. * Have limited resources. At the start of a project, an agreed amount of labor, equipment, and materials is allocated to the project. * Involve an element of risk. Projects entail a level of uncertainty and therefore carry business risk. * Achieve beneficial change. The purpose of a project is typically to improve an organization through the implementation of business change.
PROJECT LIFE CYCLE
A project life cycle is the sequence of phases that a project goes through from its initiation to its closure. The number and sequence of the cycle are determined by the management and various other factors like needs of the organization involved in the project, the nature of the project, and its area of application. The phases have a definite start, end, and control point and are constrained by time. The project lifecycle can be defined and modified as per the needs and aspects of the organization. Even though every project has a definite start and end, the objectives, deliverables, and activities vary widely. The life cycle provides the foundation of the actions that have to be performed in the project, irrespective of the specific work involved. The project life cycle generally consists of five phases. They are. PROJECT INITIATION PROJECT PLANNING PROJECT EXECUTION PROJECT CONTROL AND MONITORING PROJECT CLOSURE

## PHASES AND TEMPLATES
PROJECT PHASES AND REQUIRED TEMPLATES
INITIATION PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| PROJECT CHARTER | A project charter formally outlines a project in an organization. It covers the scope of what the project will achieve, as well as the people involved, milestones, budget, and possible risks.
PLANNING PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| PROJECT PLAN | The project plan outlines the course of work for each team member, while keeping the triple constraint of scope, schedule and budget in mind. Project plans describe the processes which will bring the proposal to life.
EXECUTION PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| SRS (DESIGN PHASE) | A software requirements specification (SRS) is a description of a software system to be developed. It lays out functional and non-functional requirements, and may include a set of use cases that describe user interactions that the software must provide.
| DEVELOPMENT LOG (BUILD PHASE) | The development log is used to make a note of all the development changes that are made during the building phase. This log will help you easily handle the different versions of code used for the development.
| TRACEABILITY MATRIX (TEST PHASE) | Traceability Matrix is a really helpful tool to capture the testcase execution progress in one place. It gives management a way to get important Data about Testing.
MONITOR AND CONTROL PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| RAID LOG | A RAID log is a project planning tool for identifying key (R)isks, (A)ssumptions, (I)ssues, and (D)ependencies. At the beginning of the venture, the project team identifies events, activities, and individuals that will or could impact on the successful completion of the project. The RAID log focuses on four key areas: Risks – events that can have an adverse impact if they occur. Assumptions – things you assume are in place which contribute to the success of the project. Issues – current matters that need to be considered and addressed by the group. Dependencies – other projects or triggers that your project depends on, or are a beneficiary of your project outcomes.
CLOSURE PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| LESSONS LEARNED | Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project. They help others learn from the project team’s experience.
SYSTEM GUIDE

## PROJECT CHARTER
PROJECT CHARTER
| DOCUMENT VERSION: 1.0 | INSTRUCTION SHEET INSTRUCTION TO USE THE PROJECT CHARTER TEMPLATE • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/ instructions provided in the template. The data/ instruction provided is only for reference purposes.
GENERAL PROJECT INFORMATION
PROJECT NAME | Job Cloud
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 31/07/2020
ESTIMATED COST
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main objective of the project is to develop an online job portal where employers can post jobs and job seekers can apply for the jobs. Job Cloud, as a job portal will help the interns/ employees of Cloud Counselage to secure a job on the successful completion of their internships/ programs.
BUSINESS CASE | Over the years, Cloud Counselage has been on a mission to develop and groom freshers and professionals PAN India to become IT and Management pioneers. To accomplish this mission, we have come up with a solution, a job portal that will list down the jobs available in major companies across India. Also, one of the success criteria of career services that Cloud Counselage offers is to get our interns placed in a job of their interest with us or with our partner companies and we will, therefore, ensure that the interns of Cloud Counselage will be given the priority for the jobs over the others and these jobs will be procured using the Job Cloud platform.
GOALS/METRICS | To create a trusted Job Portal which is going to serve as as best platform for major companies to post their jobs.
EXPECTED DELIVERABLES | A Job Portal with features that are going to benefir both the interns, job seekers and the recruiters.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Apply for a job, manage applied jobs, job packages (Employee roles)
OUTSIDE OF SCOPE | To have a video resume upload option in the portal
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Chris, Adam, Catherine
SUPPORT RESOURCES | Laptops,
COST ALLOCATION
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER | Your name
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Techical risk:Unmet requirements-forgetting to include a single requirement can cost us time & budget overhead, or worse, poor website quality. Resource risk:Uncertainty in resource availability: Interns might go on leave on commencement of university exams. Due to the COVID-19 outbreak, the exact examination dates are not available.On team change over, new members needs to get trained and it's time-consuming.Also, the current team members lack knowledge in back-end development. This might result in the escalation of project completion.
ASSUMPTIONS | Job Cloud will help all the CC interns to get a job.
CONSTRAINTS | Very stringent time for the completion of the project.

## PROJECT PLAN
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Jayanth G S
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1

## SRS DOCUMENT
SOFTWARE REQUIREMENT SPECIFICATION DOCUMENT
|  | DOCUMENT VERSION 1.0 | Instruction to use the SRS document template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.
| PROJECT NAME | Job Cloud
| PROJECT MANAGER | Jayanth GS
INTRODUCTION
| BACKGROUND | Over the years, Cloud Counselage has been on a mission to develop and groom freshers and professionals PAN India to become IT and Management pioneers. To accomplish this mission, we have come up with a solution, a job portal that will list down the jobs available in major companies across India. Also, one of the success criteria of career services that Cloud Counselage offers is to get our interns placed in a job of their interest with us or with our partner companies and we will, therefore, ensure that the interns of Cloud Counselage will be given the priority for the jobs over the others and these jobs will be procured using the Job Cloud platform.
| PROJECT OVERVIEW | The online job portal system is a package to be used by agencies to improve the efficiency of the business. The system provides job catalog and information to members and helps them to decide on the jobs to apply. The admin can keep the jobs updated all the time for the members.
| HARDWARE REQUIREMENTS | Minimum Hardware Requirements -- RAM: 512 MB or more. Processor: Pentium – IV onwards. Hard Disk Space: 40 GB or more. Server: Microsoft Windows Server 2019 Base ami-04a0ee204b44cc91a Microsoft Windows 2019 Datacenter edition. [English] EC2 - t2.micro (Variable ECUs, 1 vCPUs, 2.5 GHz, Intel Xeon Family, 1 GB memory, EBS only. Root Volume = 30 GB General-Purpose Solid-State Drive, 100/3000 IOPS
| SOFTWARE REQUIREMENTS | Software Requirements -- Operating System: Windows. Internet Browser: Chrome, Mozilla Firefox, Internet Explorer. Front-end: HTML 5, CSS, JavaScript, React (16.13.1 Web Framework). IDE: preferred Visual Studio CODE. Backend: NodeJS, MongoDB (4.2.6). AWS EC2.
| CONSTRAINTS | Very stringent time for the completion of the project.
| ASSUMPTIONS | Job Cloud will help all the CC interns to get a job.
DEPENDENCIES
FUNCTIONAL REQUIREMENTS
The list of examples of functional requirements includes: Business Rules Transaction corrections, adjustments, and cancellations Administrative functions Authentication Authorization levels Audit Tracking External Interfaces Certification Requirements Reporting Requirements
NON-FUNCTIONAL REQUIREMNTS
Usability Legal or Regulatory Requirements Reliability Performance
EXTERNAL INTERFACE REQUIREMENTS
External interface requirements are types of functional requirements. They’re important for embedded systems. And they outline how your product will interface with other components. There are several types of interfaces you may have requirements for, including: User Hardware Software Communications
TECHNOLOGY USED
Express: Express is a web application framework for Node.js, another MERN component. Instead of writing full web server code by hand on Node.js directly, developers use Express to simplify the task of writing server code. The Express framework is designed for building robust web applications and APIs. It’s known for its fast speed and minimalist structure, with many features available as plugins. React: React is a JavaScript library for building user interfaces. React anchors the MERN stack. In a way, it’s the defining feature of the stack. Node.js: Node.js is a cross-platform JavaScript runtime environment. It’s designed to build scalable network applications and can execute JavaScript code outside of a browser.
FEASIBILITY STUDY
A feasibility study is performed, which determines whether the solution considered to accomplish the requirements is practical and workable in the software. Information such as resource availability, cost estimation for software development, benefits of the software to the organization after it is developed and cost to be incurred on its maintenance are considered during the feasibility study. The objective of the feasibility study is to establish the reasons for developing the software that is acceptable to users, adaptable to change and conformable to established standards.

## DEVELOPMENT LOG
DEVELOPMENT LOG
Instruction to use the development log template: • All fields must be duly filled • The descriptions for what is to be filled in each of the fields are provided in the template. • Clear all the sample data/ instructions provided in the template. The data/ instruction provided is only for reference purposes. • Select the current version of the feature you are working on from the drop-down list in the “versions” field. • The status of development can be mentioned in the “development status” field. Three options are available for selection. If the development process is completed, please select “ completed” from the drop-down menu. If you are working on developing the application, please select “in progress” from the drop-down menu. If the development is stopped for some reason, select “paused’ from the drop-down menu.
PROJECT NAME | Job Cloud |  |  | DOCUMENT VERSION | 1 |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID |  |  |  | PROJECT START DATE | 15/06/2020
PROJECT MANAGER | Jayanth G S |  |  | PROJECT END DATE | 31/07/2020
PLEASPLEASE REMOVE THE CONTENTS IN THE WHITE SPACE ON THE TABLE BEFORE START WORKING ON THE TABLE. THE DATA PROVIDED IS ONLY FOR REFERENCE PURPOSEE REMOVE THE CONTENTS IN THE WHITE SPACE ON THE TABLE BEFORE START WORKING ON THE TABLE. THE DATA PROVIDED IS ONLY FOR REFERENCE PURPOSE
PLEASE REMOVE THE CONTENTS IN BLUE ITALIC FONT BEFORE START WORKING ON THE TABLE. THE DATA PROVIDED IS ONLY FOR REFERENCE PURPOSE. SELECT THE VERSION YOU ARE WORKING ON FROM THE DROP DOWN MENU. DEPENDING ON THE DEVELOPMENT STATUS, SELECT THE APPROPRIATE STATUS FROM THE DROP DOWN MENU PROVIDED. THE REVIEW STATUS CAN BE SELECTED FROM THE DROP DOWN MENU.
SL NO | FEATURE NAME | VERSIONS | VERSION CREATION DATE | VERSION LINK | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Navigation bar | VERSION 1 | 15/06/2020 | provide github link | In the new version, a notification icon has been added to the navigation bar. | COMPLETED | REVIEWED

## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 1 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: |  |  | Project Id: |  | Project Manager: |  |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 0 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: |  | Project Team Lead: |  |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 2 |  |  |  |  | 1
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to do required maintenance on time. | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. | Project Manager | High |  | Open | Risk
2 | Risk | Long supply delivery time | Impact on project schedule | Search for vendors who will deliver the resources on timeand within the proposed budget. | Project Manager | Critical |  | Closed | Assumption
3 | [8 empty] | Issue
4 | [8 empty] | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24

## TEST PLAN
TEST PLAN
Instruction to use the test plan template: • All fields must be duly filled • On completion of the document, please get it reviewed from your project manager/supervisor • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.
PROJECT NAME | Job Cloud
PROJECT ID
PROJECT MANAGER | Jayanth G S
INTRODUCTION
Brief introduction of the test strategies, process, workflow and methodologies used for the project
SCOPE
IN SCOPE
Scope defines the features, functional or non-functional requirements of the software that will be tested
OUT OF SCOPE
Out Of Scope defines the features, functional or non-functional requirements of the software that will NOT be tested
QUALITY OBJECTIVE
Here make a mention of the overall objevtie that you plan to achive withou your testing Some objectives of your testing project could be • Ensure the Application Under Test conforms to functional and non-functional requirements • Ensure the AUT meets the quality specifications defined by the client • Bugs/issues are identified and fixed before go live
ROLES AND RESPONSIBILITIES
Detail description of the Roles and responsibilities of different team members like • QA Analyst • Test Manager • Configuration Manager • Developers • Installation Team Amongst others
TEST METHODOLOGY
OVERVIEW
Mention the reason of adopting a particular test methodology for the project. The test methodology selected for the project could be • WaterFall • Iterative • Agile • Extreme Programming
TEST LEVELS
Test Levels define the Types of Testing to be executed on the Application Under Test (AUT). The Testing Levels primarily depends on the scope of the project, time and budget constraints.
BUG TRIAGE
The goal of the triage is to • To define the type of resolution for each bug • To prioritize bugs and determine a schedule for all “To Be Fixed Bugs’.
TEST COMPLETENESS
Here you define the criterias that will deem your testing complete. For instance, a few criteria to check Test Completeness would be • 100% test coverage • All Manual & Automated Test cases executed • All open bugs are fixed or will be fixed in next release
TEST DELIVERABLES
Here mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle. Here are the sample deliverables • Test Plan • Test Cases • Requirement Traceability Matrix • Bug Reports • Test Strategy • Test Metrics • Customer Sign Off
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Make a list of Tools like • Requirements Tracking Tool • Bug Tracking Tool • Automation Tools Required to test the project
TEST ENVIRONMENT
It mentions the minimum hardware requirements that will be used to test the Application. Following software’s are required in addition to client-specific software. • Windows 8 and above • Office 2013 and above • MS Exchange, etc.
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS

## TRACEABILITY MATRIX
TRACEABILITY MATRIX
PROJECT NAME | [5 empty] | TEST CASE COUNT | 0
DOCUMENT VERSION NUMBER | [5 empty] | PASSED | 0
PROJECT MANAGER | [5 empty] | FAILED | 0
EXECUTED BY | [5 empty] | SKIPPED | 0
SL.NO | TEST CASE | TEST INPUT DATA | TEST PROCEDURE | EXPECTED RESULT | ACTUAL RESULT | STATUS | COMMENTS | Instruction to use the traceability matrix template: • All fields must be duly filled • On completion of the document, please get it reviewed from your project manager/supervisor • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.
| MENTION THE TEST CASE FOR TESTING THE PRODUCT | ENTER THE INPUT DATA FOR TESTING THE PRODUCT | SELECT THE TESTING METHOD. FOR REFERENCE, THE DIFFERENT TYPES OF COMMONLY USED TESTING IS PROVIDED IN THE PROJECT METHODOLOGY DOCUMENT | MENTION THE EXPECTED RESULT AFTER THE PRODUCT IS TESTED | ENTER THE ACTUAL RESULT OBTAINED AFTER TESTING THE PRODUCT |  | ENTER ANY ADDITIONAL COMMENTS REGARDING THE PROCEDURE IF ANY
PLEASE REMOVE THE CONTENTS IN BLUE ITALIC FONT BEFORE START WORKING ON THE TABLE. THE DATA PROVIDED IS ONLY FOR REFERENCE PURPOSE

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0 | [9 empty] | Instruction to use the lessons learned document template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.
PROJECT NAME | Job Cloud |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 21/03/2020 | Test of API connection was missed in QA,which meant that an issue with the connection was not picked. | Technical | None | Add a new test case for this test in QA environment. | Request additional test case from test manager and inform PMO. | Project Manager | Closed
2 | 2020-05-03 | Agreeing the rating for defects in advance avoided facilitated meant that some cosmetic issue could be fixed post go live. | Technical | Early in UAT issues that weren't blocking were logged as defects. | During project initiation agree and document how issues/defects will be rated and define which issues will not be blocking for go live. | Share lessons with PMO and suggests amended to the project initiation process. | Project Manager | In Progress

## SYSTEM GUIDE
SYSTEM GUIDE
Instruction to use the system guide template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.
PROJECT NAME |  |  | PREPARED BY
PROJECT ID |  |  | REVIEWED BY
PROJECT MANAGER |  |  | APPROVED BY
PROJECT DESCRIPTION
<< Provide a short description of the project. >>
PROJECT REQUIREMENTS
<< Provide a list of the requiremnets for the project development. >>
SYSTEM OVERVIEW
DESCRIPTION | << Provide a detailed description of the technical architecture (infrastructure) including how each piece fits in to the overall solution. >>
IMPORTANT NOTES | << Each project usually contains unique characteristics which are important to convey to the various Operational groups. Identify any project related anomalies learned during development and testing. For example information can be included on the following: Public Safety Issues, Show Stoppers, Compatibility Matrices / Dependencies, Information Classification Warnings (Data Sensitivity). >>
HOURS OF AVAILABILITY | << What are the hours of system availability? When the system can be brought down for maintenance? >>
CRITICAL TIME FRAMES | << List any known critical periods for this system. Critical Periods are often a factor in scheduling downtime, change management windows or assessing criticality of an outage. >>
APPLICATION ARCHITECTURE
<< Provide a brief description of the application architecture and all of it’s components >>
DEVELOPMENT TOOLS
TOOL USED | PURPOSE
<< List the standard development tools used to develop and maintain the application. >> | << Briefly describe their purpose. >>
SOURCE CODE/EXECUTABLE FILES
SOURCE CODE DESCRIPTION | LOCATION | COMMENTS
<< Source code desc 1 >> | << Provide the location of source code / executable files >> | << Provide any other notable information >>
ADDITIONAL COMMENTS
<< Provide any additional comments or other notable information in this section. If there is information that does not fit into any of the categories above, then use this section as a place holder. >>

## GoLive Checklist
GO LIVE CHECKLIST
Please click on the attached word document to access the go live checklist.